## Instructions
IT risk assessment template: risk register (The NetSys Group, original template)
Purpose: a working register of the IT and cybersecurity risks a small or mid-size business has identified, with a simple 1 to 5 likelihood and impact score, the evidence behind each entry, an owner and a decision.
How to use it
1. List assets and processes the business depends on: email and files, line-of-business systems, backups, payments, devices, internet, key vendors, people.
2. For each, name a specific threat and the weakness that makes it plausible. 'Ransomware' alone is not an entry; 'ransomware encrypts the server and the only backup copy because the copy is on a reachable share' is.
3. Record the existing control and the evidence you looked at. An entry without evidence is an opinion.
4. Score likelihood and impact from 1 to 5 using the Scales sheet. The Score column multiplies them and the Rating column labels the result (Low 1 to 6, Medium 8 to 12, High 15 to 25).
5. Decide: Accept, Mitigate, Transfer or Avoid. Name one owner and a due date. Re-score the expected residual risk after the action.
6. Review the register quarterly and after any major change (new system, office move, provider change, incident). Record the review date on the Review log sheet.
What the score means, and what it does not
The score is ordinal: it ranks entries against each other so the business fixes the right things first. A 20 is not 'twice as likely' as a 10, and no score here is a measured probability of a breach. Treat the register as a planning aid that makes decisions visible, not as a prediction. The approach follows the common likelihood-and-impact structure described in NIST SP 800-30 Rev. 1, Guide for Conducting Risk Assessments (checked on November 7, 2026, https://csrc.nist.gov/pubs/sp/800/30/r1/final), simplified for a small business.
Vendor risks: this register holds one line per important vendor. The detailed vendor questionnaire and vendor risk register are a separate template at https://www.netsysgroup.com/blog/vendor-security-questionnaire-template
Rows marked as examples describe a fictional 25-person firm and no real business. Delete them before use.

## Scales
Score | Likelihood: how plausible in the next 12 months, given current controls | Impact: what it would do to the business
1 | Rare: hard to imagine with the controls in place; no known weakness | Negligible: minor inconvenience; no data exposed; recovered within an hour
2 | Unlikely: possible but needs unusual conditions | Minor: a few hours lost or a small cost; no sensitive data exposed
3 | Possible: a known weakness exists and the threat is common | Moderate: a day or more of disruption, a notifiable exposure of a few records, or a cost the business feels
4 | Likely: the weakness is exposed to common attacks or has already caused near misses | Major: several days of disruption, regulated data exposed, insurance claim, customer notifications
5 | Almost certain: active exploitation is known or the condition recurs | Severe: the business cannot operate, large regulated exposure, legal or contractual consequences that threaten the firm
Rating bands used by the Register sheet: Low 1 to 6, Medium 8 to 12, High 15 to 25. Products of two 1 to 5 scores can only take the values 1, 2, 3, 4, 5, 6, 8, 9, 10, 12, 15, 16, 20, 25.

## Register
ID | Asset or process | Threat | Weakness that makes it plausible | Existing control | Likelihood (1-5) | Impact (1-5) | Score | Rating | Evidence reviewed | Owner | Decision | Planned action | Due date | Status | Residual likelihood | Residual impact | Residual score | Last reviewed | Notes
R-01 | Microsoft 365 tenant (email, files) | Account takeover by phishing | MFA enforced for staff but not for two shared mailboxes and one service account | MFA on named user accounts; email filtering; annual training | 4 | 5 |  |  | Entra sign-in logs; conditional access policy export 2026-10-28 | IT provider | Mitigate | Enforce MFA by policy on every account; convert shared mailboxes to no sign-in; review service account | 2026-11-30 | In progress | 2 | 5 |  | 2026-11-05 | Fictional example (25-person firm)
R-02 | File server backups | Ransomware encrypts server and backup copy | Only backup copy is on a network share reachable from user PCs; no restore tested since 2025 | Nightly backup job; EDR on server | 3 | 5 |  |  | Backup console screenshot; job history; last restore test record | IT provider | Mitigate | Add immutable off-site copy; test a restore and time it; monthly restore test | 2026-12-15 | Open | 2 | 3 |  | 2026-11-05 | Fictional example (25-person firm)
R-03 | Six Windows 10 PCs | Exploitation of an unpatched operating system | Windows 10 reached end of support on October 14, 2025; no security updates | EDR installed; PCs on the staff network | 4 | 4 |  |  | Device inventory export 2026-10-28 | Operations manager | Mitigate | Replace or upgrade all six by year end; isolate until replaced | 2026-12-31 | Open | 1 | 4 |  | 2026-11-05 | Fictional example (25-person firm)
R-04 | Payroll platform (vendor hosted) | Vendor breach exposes staff financial data | Vendor screening not done; contract has no breach notification term | Vendor holds a SOC 2 Type 2 report (not yet reviewed) | 2 | 4 |  |  | Contract; vendor questionnaire (pending) | Office manager | Mitigate | Run the vendor security questionnaire; obtain the SOC 2 report; add notification and DPA terms at renewal | 2027-01-31 | Open | 2 | 3 |  | 2026-11-05 | Fictional example (25-person firm)
R-05 | Office internet connection | Carrier outage stops phones and cloud apps | Single carrier; no failover; staff can work from home on mobile hotspots | Documented work-from-home procedure | 3 | 2 |  |  | Carrier contract; outage log (two outages in 12 months) | Managing partner | Accept | Accept for now; revisit if a second outage over four hours occurs or when the lease renews | 2027-06-30 | Accepted | 3 | 2 |  | 2026-11-05 | Fictional example (25-person firm)
R-06 | Former staff accounts | Ex-employee or attacker uses a still-enabled account | No offboarding checklist; two enabled accounts for people who left in 2026 | Manager emails IT when someone leaves | 3 | 4 |  |  | Entra user export compared with HR list 2026-10-28 | Office manager | Mitigate | Disable the two accounts today; adopt a same-day offboarding checklist; quarterly account review | 2026-11-14 | In progress | 1 | 4 |  | 2026-11-05 | Fictional example (25-person firm)
R-07 | Laptops used off site | Lost or stolen laptop exposes client files | Disk encryption not confirmed on four older laptops | Device PIN; Intune enrollment for most devices | 2 | 4 |  |  | Intune encryption report | IT provider | Mitigate | Confirm BitLocker on all laptops; enable remote wipe; retire the two laptops that cannot encrypt | 2026-12-15 | Open | 1 | 2 |  | 2026-11-05 | Fictional example (25-person firm)
R-08 | Wire transfers | Business email compromise redirects a payment | Payment changes accepted by email; no call-back rule | Two people approve payments over a threshold | 3 | 5 |  |  | Finance procedure; recent vendor change requests | Controller | Mitigate | Require a call-back to a number on file for any bank detail change; add to finance procedure; brief staff | 2026-11-21 | In progress | 1 | 5 |  | 2026-11-05 | Fictional example (25-person firm)

## Heat map
Count of register entries by likelihood (rows) and impact (columns). Uses current scores, not residual.
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5
4
3
2
1
Red: High (15 to 25). Amber: Medium (8 to 12). Green: Low (1 to 6). The map ranks; it does not predict.

## Summary
Entries
Rated High
Rated Medium
Rated Low
Decision: Mitigate
Decision: Accept
Decision: Transfer
Decision: Avoid
Actions past due
High entries without an owner
Counts rank the work. They are not a measure of breach probability or an audit result.

## Review log
Review date | Reviewed by | Trigger (quarterly, incident, change) | Entries added | Entries closed | Notes
2026-11-05 | Managing partner and IT provider | Initial register (fictional example) | 8 | 0 | Delete this row before use