## Instructions
Penetration test findings and retest tracker (The NetSys Group, original template)
Purpose: one row per finding from a penetration test report, tracked from issue to verified fix.
This workbook is a tracking aid. It is not evidence that a penetration test occurred; the testing firm's report and its evidence files are.
How to use it
1. Copy each finding from the report into the Findings sheet: ID, title, severity, score if the report used CVSS, affected asset and the report's fix.
2. Assign an owner and a due date. The Rating column and the Summary sheet update themselves.
3. When the owner reports a fix, enter the fix date and ask the tester for a retest. Record the retest date, result and the evidence ID the tester supplies.
4. A finding is closed only when Retest result is Fixed, or when a named approver records an Accepted decision with a review date.
5. Keep the evidence files in a folder named by finding ID so the spreadsheet stays light.
Severity scale reference: the Severity scale sheet reproduces the CVSS v4.0 qualitative ranges published by FIRST (checked on November 7, 2026). Use it when the report scores with CVSS; otherwise use the report's own labels and state them.
Rows marked EXAMPLE are fictional and describe no real business. Delete them before use.

## Findings
Finding ID | Title | Severity | CVSS v4.0 score (if used) | Affected asset | Found on | Fix from report | Owner | Due date | Status | Fix reported | Retest date | Retest result | Evidence ID | Days open | Notes
F-01 | EXAMPLE: Expired administrator account still accepts remote desktop logins | High | 8.2 | rds.example-fictional.test | 2026-10-30 | Disable and delete the account; enforce MFA by policy on every gateway account; quarterly account review | IT provider | 2026-11-13 | Fix reported | 2026-11-05 |  |  | E-01-a, E-01-b |  | Fictional sample from the report template
F-02 | EXAMPLE: Marketing site exposes a backup archive in a public folder | Medium | 5.3 | www.example-fictional.test/backup/ | 2026-10-30 | Remove the archive, block directory listing, move backups off the web root | Web agency | 2026-11-20 | Open |  |  |  | E-02-a |  | Fictional sample
Formulas:
Days open = IF([Found on]="","",IF(OR([Retest result]="Fixed",[Status]="Closed",[Status]="Accepted"),"",TODAY()-[Found on]))

## Summary
Severity | Total | Open | In progress | Fix reported | Retest requested | Closed or accepted
Critical
High
Medium
Low
Informational
Total
Verified fixed at retest
Past due and not fixed
Counts are a tracking aid. They do not measure risk and are not an audit result.

## Severity scale
Rating | CVSS v4.0 score | Note
None | 0.0 | Qualitative severity rating scale from the FIRST CVSS v4.0 specification.
Low | 0.1 to 3.9
Medium | 4.0 to 6.9
High | 7.0 to 8.9
Critical | 9.0 to 10.0
Source: https://www.first.org/cvss/v4-0/specification-document (checked on November 7, 2026). A base score describes technical severity; the report should also state the business context that moved a rating.