## Instructions
Vendor risk register (The NetSys Group, original template)
Purpose: one row per outside company that holds your data, connects to your systems or runs a process you cannot do without. The register records the tier, the screening status, the findings, the exceptions you accepted, who approved and when the next review is due.
How to use it
1. List every vendor you pay for software, hosting, IT, payroll, accounting, phones or data handling. Add the business owner who manages the relationship.
2. Set Data access and System access from the drop-downs. The Suggested tier column proposes a tier from those two answers plus the Critical to operations flag; override it in the Tier column with a reason.
3. Send the questionnaire that matches the tier (see the Vendor security questionnaire workbook). Track status in Questionnaire status.
4. Record findings and any exceptions you choose to accept, each with an expiry date. The Approver is the person with authority to accept that risk for the business, not the person who ran the review.
5. Review cadence by tier: Tier 1 every 12 months, Tier 2 every 24 months, Tier 3 at renewal or on a change in what the vendor does for you. Next review is calculated from the last review date and the cadence.
A register entry marked Approved means the business accepted the vendor after screening. It does not certify the vendor, and it does not transfer your legal duties to protect data.
Rows marked EXAMPLE are fictional and describe no real business or vendor. Delete them before use.

## Tiering guide
Tier | Typical vendors | Trigger | Screening expected | Review cadence
1 | IT provider with admin rights, payroll and HR platform, practice or case management system, cloud file storage, EDR or backup vendor, any vendor holding regulated data (health, card, financial, personal) or with integration or admin access | Regulated or confidential data, OR admin or integration access to our systems, OR the business stops within a day if the vendor is down | Full questionnaire; SOC 2 Type 2 or equivalent; penetration test summary; insurance certificate; DPA or BAA; subprocessor list; contract security terms | 12 months
2 | Line-of-business software with internal data, marketing and CRM tools, phone system, website host and agency, accounting software without bank access | Internal or confidential data without regulated categories, OR user-level access, OR a disruption the business can work around for a few days | Full or shortened questionnaire; one independent evidence item (SOC 2, ISO 27001 or pen test summary); insurance certificate; DPA where personal data is involved | 24 months
3 | Vendors with no access to our data or systems, or public information only: office supplies, facilities, printing, most professional services without data | No data access and no system access, and the business can switch suppliers easily | Short questionnaire or none; confirm the contract has basic confidentiality terms | At renewal or on change

## Register
Vendor | Service provided | Business owner | Data access | System access | Critical to operations | Suggested tier | Tier (final) | Tier reason | Questionnaire status | Findings | Exceptions accepted | Exception expiry | Approver | Decision | Decision date | Last review | Cadence (months) | Next review | Contract or renewal date | Notes
EXAMPLE: Harborline Payroll Co. | Payroll and HR records | Office manager | Regulated (PHI, PCI, PII or financial) | Integration | Yes |  | 1 | Holds staff financial and personal data; connects to the accounting system | Reviewed | No penetration test summary available; MFA enforced; SOC 2 Type 2 received (period ended 2026-06-30, two exceptions on change management) | Pen test summary to be supplied by 2027-02-28; vendor to notify of changes to the two SOC 2 exceptions | 2027-02-28 | Managing partner | Approved with exceptions | 2026-11-05 | 2026-11-05 | 12 |  | 2027-07-01 | Fictional sample
EXAMPLE: Brightfield Web Studio | Website hosting and maintenance | Marketing lead | Internal only | Admin | No |  | 2 | Admin access to the public website only; no customer data on the site | Sent |  |  |  |  | Pending |  |  | 24 |  | 2027-03-31 | Fictional sample
EXAMPLE: Cedar Office Supplies | Stationery and consumables | Office manager | None | None | No |  | 3 | No data or system access | Not required |  |  |  | Office manager | Approved | 2026-11-01 | 2026-11-01 | 36 |  | 2027-11-01 | Fictional sample
Formulas:
Next review = IF(OR([Last review]="",[Cadence (months)]=""),"",EDATE([Last review],[Cadence (months)]))

## Exceptions log
Vendor | Exception (what is missing or not met) | Why accepted | Compensating control | Approver | Accepted on | Expires | Status | Closed on
EXAMPLE: Harborline Payroll Co. | No external penetration test summary available | Vendor holds a current SOC 2 Type 2; pen test program planned for Q1 2027 | Integration account limited to read access; quarterly export review | Managing partner | 2026-11-05 | 2027-02-28 | Open

## Summary
Tier | Vendors | Not started | Sent | Received | Reviewed | Approved with exceptions
1
2
3
Reviews overdue
Exceptions past expiry
Counts track the screening program. They are not a measure of vendor security.